## Coria Burndown Chart Template
SPRINT BURNDOWN CHART
| Backlog Item ID | User Stories / Bugs |  | Jul 11th | Jul 12th | Jul 13th | Jul 14th | Jul 15th | Jul 18th | Jul 19th | Jul 20th | Jul 21st | Jul 22nd
|  |  | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| 123456 | Example Product Backlog Item (PBI) Estimated During Sprint Planning | 5 | Jul 12th Day 2: 5 | Legend
| 123457 | Example Bug Included at the Beginning of Sprint Planning | 2 | Jul 20th Day 8: 2
| 123458 | Example PBI Entered After Sprint Planning (On Day 3) |  | Jul 13th Day 3: -3; Jul 20th Day 8: 3 |  | = | Missing at Start
| 123459 | Example Bug Entered After Sprint Planning (On Day 5) |  | Jul 15th Day 5: -2; Jul 19th Day 7: 2 |  | = | Added to Sprint
| 123460 | Example PBI Entered After Sprint Planning (On Day 6) |  | Jul 18th Day 6: -3; Jul 22nd Day 10: 3 |  | = | Projected Value
|  | Remaining Effort | 7 | 7 | 2 | 5 | 5 | 7 | 10 | 8 | 3 | 3 | 0
|  | Ideal Trend | 7 | 6.3 | 5.6 | 4.9 | 4.2 | 3.5 | 2.8 | 2.1 | 1.4 | 0.7 | -1.1102e-15
Note on E5: Coria: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on G6: Coria: Use a positive number to indicate that the item is complete.
Note on H8: Coria: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on R8: Coria: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on J9: Coria: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on L9: Coria: Use a positive number to indicate that the item is complete.
Note on R9: Coria: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on K10: Coria: Use a negative number to indicate that your level of effort just went up.
Note on O10: Coria: Use this formatting to indicate that you are projecting a number that is not yet final.
Note on R10: Coria: If you are only partway through a Sprint, but would like to project a completion or perform what-if analysis, use this formatting to indicate something is not yet final.